HAVING A MEETING …. WHERE DO YOU START?

Below is a list of questions to get you ready to complete a ITB/RFQ/RFP for planning your next meeting.  You could gather this information from previous planners, if the meeting is an annual meeting, you could ask information of the registration form, ask your agency sponsor that is conducing the meeting or ask who is most familiar with the group such as an advisory committee.

What are the purpose and outcomes for the meetings?

Why?

Why now? (This may give you insight as to why it must be at this time)

Educational Program

Retreat (Is this s strategic planning retreat?)

Imperative and Desirables (What must absolutely be addressed in meeting and 				what would you desire to have in the meeting.)

Who will attend and what do you need to know about them?

How Many People

Educational Backgrounds

Levels and Functions in Organization

Lines of Authority (If asking for input during meeting, please may not talk 				openly if bosses are there)

Relationships (Amongst attendees/agencies)

Issues (Will this have media coverage? Protesters?)

Gender (Consider catering, location of rooms, temps in room, location of 				property, optional activities, bathroom arrangements, if all male 					attendees you may need to get male speakers.)

Age (Consider learning styles, faster or slower pace, dressing requirements, see 				gender considerations.)

ADA Issues

Voluntary or Mandatory

Lodging Needs

Level of Expectation (Used to staying at medium class hotels and would be 				uncomfortable at ritzy hotel or higher class and never stayed at medium 				class hotel.

Do they know why they’re attending? (Are they prisoners in a mandatory 			meeting, will the group be negative because they do not want to be 			there?)

Is there a history for this program?

Documentation (History of the meeting)

Evaluations (From previous meetings/post conference reports)

Suggestions (Previous meetings/post conference reports.)

What is the budget? (In accordance with PPM49)

What is the program format? (Need to know for space planning and room designs 				during the day, do you need display space, special equipment?)

Keynote/General Sessions

Seminar

Breakout Sessions

Panel Discussions

Continuing Education Units

What type of venue?

Consistent With Purpose

Agency Facilities

Hotels

Conference Centers

Restaurant

Who will be working with you for planning?

Sponsor

Advisory Committee

Volunteers

Contract Planner

Develop a work (project) plan.

Description of Scope (What is within and not within scope)

Activities to Task Level (Draft ITB/RFQ/RFP get approval, send, review, etc.)

Assign Responsibility

Timeline (Framed with lag time)

Gantt Chart (Sequenced or concurrent)

Event specification guide (APEX tools)

Utilize CVBs (Convention & Visitor’s Bureau)

RFP

Contact SGMP Member Properties

Create and update event notebook

Keep the sponsor informed

Conclusion:

By asking the right questions and up front, breaking down the planning to the task level, utilizing a available resources, and continually updating the plan, you increase the likelihood of having a successful meeting.

PROJECT MANAGEMENT TIMELINE

PROJECT: ____________________________________

MANAGER: __________________________________		COMPLETION DATE: ________________

| Deliverable/Activity | Responsible Person/Group | Timeline | Completion |
| --- | --- | --- | --- |
|  |  | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Date |
| 1.0 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.1 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.2 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.3 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.4 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.5 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.6 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.7 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.8 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.9 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.0 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.1 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.2 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.3 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.4 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.5 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

GANTT CHART

| Tasks | Assigned To: | Timeline | Actual Completion Date |
| --- | --- | --- | --- |
|  |  | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 |  |
| 1.1 |  |  |  |  |  |  |  |
| 1.2 |  |  |  |  |  |  |  |
| 1.3 |  |  |  |  |  |  |  |
| 1.4 |  |  |  |  |  |  |  |